## WBS with Gantt Chart
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE
PROJECT MANAGER
COMPANY NAME
DATE | [6 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[6 empty] | COMPLETE | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception & Initiation
1.1 | Project Charter | Leon W | 2022-03-12 | 2022-03-15 | 3 | 100%
1.1.1 | Project Charter Revisions | Kylie R | 2022-03-15 | 2022-03-16 | 1 | 100%
1.2 | Research | Pete S | 2022-03-15 | 2022-03-21 | 6 | 90%
1.3 | Projections | Steve L | 2022-03-16 | 2022-03-22 | 6 | 40%
1.4 | Stakeholders | Allen W | 2022-03-17 | 2022-03-22 | 5 | 70%
1.5 | Guidelines | Malik M | 2022-03-18 | 2022-03-22 | 4 | 60%
1.6 | Project Initiation | Malik M | 2022-03-23 | 2022-03-23 | 0 | 50%
2 | Project Definition & Planning
2.1 | Scope & Goal Setting | Steve L | 2022-03-24 | 2022-03-28 | 4 | 5%
2.2 | Budget | Allen W | 2022-03-29 | 2022-04-02 | 4 | 30%
2.3 | Communication Plan | Malik M |  |  | 0 | 0%
2.4 | Risk Management | Malik M |  |  | 0 | 0%
3 | Project Launch & Execution
3.1 | Status & Tracking | Pete S |  |  | 0 | 0%
3.2 | KPIs | Leon W |  |  | 0 | 0%
3.2.1 | Monitoring | Kylie R |  |  | 0 | 0%
3.2.2 | Forecasts | Kylie R |  |  | 0 | 0%
3.3 | Project Updates | Pete S |  |  | 0 | 0%
3.3.1 | Chart Updates | Malik M |  |  | 0 | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives | Steve L |  |  | 0 | 0%
4.2 | Quality Deliverables | Allen W |  |  | 0 | 0%
4.3 | Effort & Cost Tracking | Malik M |  |  | 0 | 0%
4.4 | Project Performance | Malik M |  |  | 0 | 0%
CLICK HERE TO CREATE IN SMARTSHEET
Formulas:
DURATION = DAYS([DUE DATE],[START DATE])

## WBS_Gantt Chart_SINGMAL_TOUR
WORK BREAKDOWN STRUCTURE WITH GANTT CHART TEMPLATE
PROJECT TITLE | TOUR TO SINGMAL
PROJECT MANAGER | V.C.CHAMUNDEESWARI
COMPANY NAME | KCS
DATE | 06/28/2019 | [7 empty] | PHASE ONE | [27 empty] | PHASE ONE | [13 empty] | WeekEnds List
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | % of TASK | Timings (hrs) | Price | WEEK 1 - June | [6 empty] | WEEK 2 - July | [6 empty] | WEEK 3 - Aug | [6 empty] | WEEK 4 - Aug | [6 empty] | WEEK 1 - Aug | [6 empty] | WEEK 2 - Sep | [6 empty] | 2019-06-29
[6 empty] | COMPLETE |  |  | MO | TU | WE | TH | FR | SA | SU | MO | TU | WE | TH | FR | SA | SU | MO | TU | WE | TH | FR | SA | SU | MO | TU | WE | TH | FR | SA | SU | MO | TU | WE | TH | FR | SA | SU | MO | TU | WE | TH | FR | SA | SU | 2019-06-30
[9 empty] | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 2019-07-06
1 | TRAVEL | [49 empty] | 2019-07-07
1.1 | Book Flight Tickets > * CHN to SING * MAL to CHN | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-06-26 | 2019-06-30 | 4 | 100% | 2 | 40000 | [42 empty] | 2019-08-03
1.2 | Book Hotels > * CHN to SING * MAL to CHN | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-06-30 | 2019-07-01 | 1 | 100% | 6 | 50000 | [42 empty] | 2019-08-04
1.3 | Apply for Visa | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-08-01 | 2019-08-09 | 8 | 0% | 2 | 10000 | [42 empty] | 2019-08-10 | bar: WEEK 3 - Aug TH 1
1.4 | Collect Visa | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-08-09 | 2019-08-09 | 0 | 0% | 4 | 0 | [42 empty] | 2019-08-11 | bar: WEEK 4 - Aug FR 9
1.5 | Travel from Chennai to Singapore | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-08-31 | 2019-09-01 | 1 | 0% | 4 | 0 | [42 empty] | 2019-08-31 | bar: WEEK 1 - Aug SA 31
1.6 | Travel from Malaysia to Chennai | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-08 | 2019-09-08 | 0 | 0% | 4 | 0 | [42 empty] | 2019-09-01 | bar: WEEK 2 - Sep SU 8
1.7 | Travel from Singapore to Malaysia | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-04 | 2019-09-04 | 0 | 0% | 1.5 | 0 | [42 empty] | 2019-09-07 | bar: WEEK 2 - Sep WE 4
1.8 | Buy Singapore Simcard | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-08-31 | 2019-08-31 | 0 | 0% | 0.25 | 10000 | [42 empty] | 2019-09-08 | bar: WEEK 1 - Aug SA 31
1.9 | 2 MRT (Metro Rail Transport) - Recharge 20 or 30 $ | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-08-31 | 2019-08-31 | 0 | 0% | 0.25 | 0 | bar: WEEK 1 - Aug SA 31
1.10 | Always have $500 cash in at Singapore | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-08-31 | 2019-09-08 | 8 | 0% | 0 | 0
1.11 | Always have $500 cash in at Malaysia | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-04 | 2019-09-08 | 4 | 0% | 0 | 0
1.12 | Always Carry Original ID card | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-08-31 | 2019-09-08 | 8 | 0% | 0 | 0
2 | STAY AT SINGAPORE
2.1 | Arab Street | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-08-31 | 2019-08-31 | 0 | 0% | 2 | 0 | bar: WEEK 1 - Aug SA 31
2.2 | Bugis Street | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-08-31 | 2019-08-31 | 0 | 0% | 2 | 0 | bar: WEEK 1 - Aug SA 31
2.3 | China Town | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-08-31 | 2019-08-31 | 0 | 0% | 2 | 0 | bar: WEEK 1 - Aug SA 31
2.4 | Little India | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-08-31 | 2019-08-31 | 0 | 0% | 2 | 0 | bar: WEEK 1 - Aug SA 31
2.5 | Sentosa Island - Universal Studios | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-01 | 2019-09-01 | 0 | 0% | 8 | 8000 | bar: WEEK 1 - Aug SU 1
2.6 | Sentosa Island - Skyline Luge | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-02 | 2019-09-02 | 0 | 0% | 2 | 2600 | bar: WEEK 2 - Sep MO 2
2.7 | Sentosa Island - S.e.a Aquarium | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-02 | 2019-09-02 | 0 | 0% | 2 | 1200 | bar: WEEK 2 - Sep MO 2
2.8 | Sentosa - Merlion Walk + Song of the sea | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-02 | 2019-09-02 | 0 | 0% | 2 | 0 | bar: WEEK 2 - Sep MO 2
2.9 | Sentosa - Cable car | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-02 | 2019-09-02 | 0 | 0% | 2 | 4000 | bar: WEEK 2 - Sep MO 2
2.10 | Night Safari Noctural Wildlife Park | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-02 | 2019-09-02 | 0 | 0% | 3 | 4200 | bar: WEEK 2 - Sep MO 2
2.11 | Gardens by the bay | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-03 | 2019-09-03 | 0 | 0% | 2 | 2420 | bar: WEEK 2 - Sep TU 3
2.12 | Singapore Flyer | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-03 | 2019-09-03 | 0 | 0% | 2 | 5500 | bar: WEEK 2 - Sep TU 3
2.13 | Marina Bay - Light Shows | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-03 | 2019-09-03 | 0 | 0% | 2 | 0 | bar: WEEK 2 - Sep TU 3
2.14 | Marina Bay - Art Science Museum | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-03 | 2019-09-03 | 0 | 0% | 2 | 4000 | bar: WEEK 2 - Sep TU 3
2.15 | Marina Bay - Sands Sky Park | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-03 | 2019-09-03 | 0 | 0% | 2 | 2040 | bar: WEEK 2 - Sep TU 3
2.16 | Palawan Beach | T.H.Krishna Kumar / V.C.Chamundeeswari |  |  | 0 | 0% |  | 0 | bar: WEEK 2 - Sep TU 3
2.17 | Siloso Beach | T.H.Krishna Kumar / V.C.Chamundeeswari |  |  | 0 | 0% |  | 0 | bar: WEEK 2 - Sep TU 3
3 | STAY AT MALAYSIA
3.1 | Batu Caves | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-04 | 2019-09-04 | 0 | 0% | 3 | 0 | bar: WEEK 2 - Sep WE 4
3.2 | Central Market - China Town | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-04 | 2019-09-04 | 0 | 0% | 2 | 0 | bar: WEEK 2 - Sep WE 4
3.3 | Menara KL Tower | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-04 | 2019-09-04 | 0 | 0% | 2 | 0 | bar: WEEK 2 - Sep WE 4
3.4 | Petronas Tower / KLCC park | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-04 | 2019-09-04 | 0 | 0% | 2 | 0 | bar: WEEK 2 - Sep WE 4
3.5 | Genting Highlands | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-05 | 2019-09-05 | 0 | 0% | 8 | 1000 | bar: WEEK 2 - Sep TH 5
3.6 | Selangor - Zeo Negara Malaysia 0- Oldest Rain Forest | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-06 | 2019-09-06 | 0 | 0% | 6 | 330 | bar: WEEK 2 - Sep FR 6
3.7 | Selangor - Fireflies and Monkey Feeding Tour | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-06 | 2019-09-06 | 0 | 0% | 2 | 7200 | bar: WEEK 2 - Sep FR 6
3.8 | Kuala Gandah Elephant Sanctury | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-07 | 2019-09-07 | 0 | 0% | 5 | 8200 | bar: WEEK 2 - Sep SA 7
3.9 | Jalan Alor - Street Food | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-07 | 2019-09-07 | 0 | 0% | 2 | 0 | bar: WEEK 2 - Sep SA 7
3.10 | Petaling Stree Market - Cheap Shopping | T.H.Krishna Kumar / V.C.Chamundeeswari | 2019-09-07 | 2019-09-07 | 0 | 0% | 3 | 0 | bar: WEEK 2 - Sep SA 7
3.11 | Gua tempurung malaysia - Cave Exploration | T.H.Krishna Kumar / V.C.Chamundeeswari |  |  | 0 | 0% |  | 0 | bar: WEEK 2 - Sep SA 7
3.12 | Titiwangsa Lake Garden - Relax place for recreational activities | T.H.Krishna Kumar / V.C.Chamundeeswari |  |  | 0 | 0% |  | 0 | bar: WEEK 2 - Sep SA 7
3.13 | Connaught Market - Only on Wednesday | T.H.Krishna Kumar / V.C.Chamundeeswari |  |  | 0 | 0% |  | 0 | bar: WEEK 2 - Sep SA 7
3.14 | Theon Hou | T.H.Krishna Kumar / V.C.Chamundeeswari |  |  | 0 | 0% |  | 0 | bar: WEEK 2 - Sep SA 7
Formulas:
DURATION = [DUE DATE]-[START DATE]+NETWORKDAYS([START DATE],[DUE DATE],2)-NETWORKDAYS([START DATE],[DUE DATE],0)

## Places to Visit
City | Day | Date | Place | Timings | Cost (Rs / per person) | Total | Comments
Singapore | 1 | Aug 31,2019 | Arab Street | Before 7 PM | 0 | 0 | Plan from 5 pm
Singapore | 1 | Aug 31,2019 | Bugis Street | 11 am to 11 pm | 0 | 0 | Singapore All Day Pass - 15000 per person. Go to places and use for 3 consecutive days
Singapore | 1 | Aug 31,2019 | China Town | Night life | 0 | 0
Singapore | 1 | Aug 31,2019 | Little India | 10 am to 12 am | 0 | 0
Singapore | 2 | Sep 1,2019 | Sentosa Island - Universal Studios | 10 am to 10 pm | 4000 | 8000
Singapore | 3 | Sep 2,2019 | Sentosa Island - Skyline Luge | 10 am to 9.30 pm | 1300 | 2600
Singapore | 3 | Sep 2,2019 | Sentosa Island - S.e.a Aquarium | 10 am to 7 pm | 600 | 1200
Singapore | 3 | Sep 2,2019 | Sentosa - Merlion Walk + Song of the sea | Opens 24/7. Till 10 pm | 0 | 0
Singapore | 3 | Sep 2,2019 | Sentosa - Cable car | 8.45 am to 10 pm | 2000 | 4000
Singapore | 3 | Sep 2,2019 | Night Safari Noctural Wildlife Park | 7.15 pm to 12 am | 2100 | 4200
Singapore | 4 | Sep 3,2019 | Gardens by the bay | 5 am to 2 am | 1210 | 2420
Singapore | 4 | Sep 3,2019 | Singapore Flyer | 8.30 am to 10.30 pm | 2750 | 5500
Singapore | 4 | Sep 3,2019 | Marina Bay - Light Shows | 8 pm to 9.30 pm | 0 | 0 | Buffer Places to Visit
Singapore | 4 | Sep 3,2019 | Marina Bay - Art Science Museum | 10 am to 7 pm | 2000 | 4000 | Buffer Places to Visit (Price here is for all exhibition; If single or double exhibition, prices will be 10 less)
Singapore | 4 | Sep 3,2019 | Marina Bay - Sands Sky Park | 9.30 am to 10 pm | 1020 | 2040 | Buffer Places to Visit
Singapore | BU |  | Palawan Beach |  | 0 | 0 | Buffer Places to Visit
Singapore | BU |  | Siloso Beach |  | 0 | 0 | Buffer Places to Visit
| 1 | Sep 4,2019 | Singapore to Malaysia | 8:00 |  |  | Bus / Flight
Malaysia | 1 | Sep 4,2019 | Batu Caves | 6 am to 21 pm | 0 | 0
Malaysia | 1 | Sep 4,2019 | Central Market - China Town | 10 am to 22 pm | 0 | 0
Malaysia | 1 | Sep 4,2019 | Menara KL Tower | 9 am to 22 pm | 0 | 0 | free tickets if go early
Malaysia | 1 | Sep 4,2019 | Petronas Tower / KLCC park | 9 am to 9 pm / 10am to 20 pm | 0 | 0
Malaysia | 2 | Sep 5,2019 | Genting Highlands | 7 am to 12 am | 500 | 1000 | Appro 1 hr from KL to Awana Skyway. Take Awana cable car to reach Skyavenue station in 10 mins. In middle stop is chin Swee for nature greens view
Malaysia | 3 | Sep 6,2019 | Selangor - Zeo Negara Malaysia 0- Oldest Rain Forest | 9 am to 17.30 om | 165 | 330
Malaysia | 3 | Sep 6,2019 | Selangor - Fireflies and Monkey Feeding Tour | Pick up at 3.30 pm | 3600 | 7200 | If book in thrillophilla. Pick up from KLCC, Bukit, China Town
Malaysia | 4 | Sep 7,2019 | Kuala Gandah Elephant Sanctury | 10 amd to 16.30 pm | 4100 | 8200
Malaysia | 4 | Sep 7,2019 | Jalan Alor - Street Food | 24 hrs | 0 | 0
Malaysia | 4 | Sep 7,2019 | Petaling Stree Market - Cheap Shopping | 10 am to 21 pm | 0 | 0
Malaysia | BU |  | Gua tempurung malaysia - Cave Exploration |  | 0 | 0 | Buffer Places to Visit
Malaysia | BU |  | Titiwangsa Lake Garden - Relax place for recreational activities | 10 am to 21 pm | 0 | 0 | Buffer Places to Visit
Malaysia | BU |  | Connaught Market - Only on Wednesday | 17 pm to 12 am | 0 | 0 | Buffer Places to Visit
Malaysia | BU |  | Theon Hou - Temple | 9 am to 18 pm | 0 | 0 | Buffer Places to Visit
Malaysia | BU |  | Selangor - Templer Park Waterfall | 09:00:00 AM to 8 pm | 2884 | 5768

## Activity_WorkPackage Hierarchy
Project or Main Deliverables | TOUR TO SINGMAL
Sub-Deliverables | VISIT TO SINGAPORE |  | VISIT TO MALAYSIA
Work Packages | TRAVEL TO SINGAPORE | STAY AT SINGAPORE | TRAVEL TO MALAYSIA | STAY AT MALAYSIA
Activities | Book Flight Tickets > * CHN to SING * MAL to CHN | Arab Street | Book Flight Tickets > * CHN to SING * MAL to CHN | Batu Caves
| Apply for Visa | Bugis Street | Apply for Visa | Central Market - China Town
| Collect Visa | China Town | Collect Visa | Menara KL Tower
| Travel from Chennai to Singapore | Little India | Travel from Chennai to Singapore | Petronas Tower / KLCC park
| Travel from Singapore to Malaysia | Sentosa Island - Universal Studios | Travel from Malaysia to Chennai | Genting Highlands
| Buy Singapore Simcard | Sentosa Island - Skyline Luge | Buy Malaysia Simcard | Selangor - Zeo Negara Malaysia 0- Oldest Rain Forest
| 2 MRT (Metro Rail Transport) - Recharge 20 or 30 $ | Sentosa Island - S.e.a Aquarium | 2 MRT (Metro Rail Transport) - Recharge 20 or 30 $ | Selangor - Fireflies and Monkey Feeding Tour
| Always have $500 cash in at Singapore | Sentosa - Merlion Walk + Song of the sea | Always have $500 cash in at Singapore | Kuala Gandah Elephant Sanctury
| Always have $500 cash in at Malaysia | Sentosa - Cable car | Always have $500 cash in at Malaysia | Jalan Alor - Street Food
| Always Carry Original ID card | Night Safari Noctural Wildlife Park | Always Carry Original ID card | Petaling Stree Market - Cheap Shopping
|  | Gardens by the bay |  | Gua tempurung malaysia - Cave Exploration
|  | Singapore Flyer |  | Titiwangsa Lake Garden - Relax place for recreational activities
|  | Marina Bay - Light Shows |  | Connaught Market - Only on Wednesday
|  | Marina Bay - Art Science Museum |  | Theon Hou
Marina Bay - Sands Sky Park
Palawan Beach
Siloso Beach